## Slide 1
ALPHA MANUFACTURING GROUP
ERP Transformation
Approach, scope, and data strategy for a 12-month go-live
Prepared for the Executive Team
Program Advisory · 17 July 2026
Date is fixed. Scope is the variable.
Notes: Framing: the board approved a replacement. Our job is to tell them what go-live actually means, what we refuse to put in it, and how leadership keeps seeing numbers throughout. The one line to remember: the date is fixed, scope is the variable.

## Slide 2
1
The age of the ERP isn't the problem
It's a symptom. Here's the disease.
80%
of custom orders eroded margin last year
We find out after we've shipped. That's a data latency problem, not a pricing problem.
2
systems of record for the same BOM
A nightly sync we already know is fragile sits between engineering and the shop floor.
0
reliable contribution margin views
Labor isn't tracked to the job, so job cost can't be trusted, so nobody owns margin.
A new ERP fixes none of this by itself. One system of record, labor on the job, and reporting we own is what fixes it.
AMG ERP Transformation | Confidential
2
Notes: If challenged: yes, the 20-year-old system is genuinely hard to maintain. But if we replace it and still don't capture labor to the job, we will have spent the budget and still not be able to answer why an order lost money. The ERP is the enabler. It is not the outcome.

## Slide 3
2
What we'll be judged on in 18 months
1
Margin transparency
Quoted vs. actual contribution margin per job, visible while the job is still open.
2
One BOM
Engineering and manufacturing read the same record. The nightly sync is retired, not improved.
3
No interruption
We ship, invoice, and close every single month throughout the transition.
4
A simpler landscape
Fewer systems, a named owner for every data domain, one set of KPI definitions.
5
An upgradable platform
Standard configuration we can take quarterly releases on without launching a project.
Explicitly NOT objectives
Replacing every system in the landscape.
Reproducing the legacy ERP's behavior in a new tool.
Touching CRM, HRIS, or payroll in this cutover.
Migrating twenty years of transaction history.
Every one of these is a real request we expect to receive, and a real way this program fails.
AMG ERP Transformation | Confidential
3
Notes: The right-hand column is the important half. Objectives everyone agrees with are easy. The non-objectives are where the program is actually won, because each one has a sponsor who will ask for it in month four.

## Slide 4
3
Phasing: three options, one recommendation
We hold the 12-month date and redefine what go-live means.
REJECTED
Big bang
Five sites, everything, month 12
One weekend, everywhere. With 80% of orders custom, a BOM or MRP failure stops shipping at five plants at once. The blast radius is the company.
REJECTED
Module-phased
Finance first, manufacturing later
Keeps legacy alive as the MRP engine, so the fragile sync survives another year. Spends the budget on the part that isn't broken.
RECOMMENDED
Site-phased
Full core each wave
All entity finance + one site's operations at M12. Remaining sites in two waves. Proves ETO on real orders at limited blast radius.
The one deliberate split
All five entities move to the new GL together at Wave 1, so consolidation lives in one place from Day 1. Sites still on legacy feed summary journals until their wave. We split at the GL boundary, not the entity boundary: it costs one temporary interface and buys us a single month-end close.
AMG ERP Transformation | Confidential
4
Notes: Expect pushback that at 200 people a big bang is manageable. Answer: it is manageable right up until it isn't, and the failure mode is five quiet loading docks. Site-phasing costs us roughly nine months of dual maintenance and one interface. That is the insurance premium, and it is cheap against a stopped shipment on capital equipment.

## Slide 5
4
The 18-month shape
Go-live at month 12 is Wave 1, not the finish line.
M0-M2
Mobilize
Sponsor and decision rights named. Data owners named. Item master and BOM cleanup starts in legacy. Auditors engaged on migration and rev-rec treatment.
M2-M6
Fit-to-standard design
Conference room pilot on five real historical orders, one with a mid-build ECN. Scope freezes at the end of M6.
M6-M11
Build and rehearse
Three mock data loads. Two mock cutovers. Mock cutover 2 includes a full trial month-end close on migrated data.
M12
Wave 1 go-live
All entity finance + the pilot site's full ETO cycle. Timed to a fiscal quarter start. Never year end.
M13-M18
Waves 2 and 3
Remaining four sites. Legacy goes read-only, then decommissions.
M18+
Value phase
CPQ, service management, advanced analytics. The things we deliberately deferred.
Scope freezes at M6. Anything raised after that goes to the Phase 2 backlog by default, not to a debate.
AMG ERP Transformation | Confidential
5
Notes: The rehearsal points matter most. Three mock loads and two mock cutovers is not padding: it is the only reason we can promise a close. If someone asks where to save money, it is not here.

## Slide 6
5
Top risks, and what we do about them
Item master and BOM data quality
Twenty years of accumulation behind a sync that already fails.
Named owner per domain. Cleanse in legacy, not in the load. Hard entry criteria per mock. Finance signs every reconciliation.
Scope creep and legacy habit
Eighty users with twenty years of muscle memory.
Fit-to-standard by default. Change board requiring an exec sponsor and a dollar figure. Contingency held by steering, not the PM.
SME capacity
200 people. The ones who know the process run the plant.
Six SMEs named, funded, backfilled, ring-fenced from M0. Availability tracked weekly as a schedule risk.
Engineer-to-order fit
Mid-build engineering change is where these programs die.
Prove it in the pilot on real orders before we build. A stage gate with authority to stop the program.
Cutover stops shipments
A quiet dock is the failure that reaches the Board.
Freeze window, pre-built safety stock, two rehearsed cutovers, written rollback with a named owner and a fixed go/no-go hour.
Risk 6, and we'll be blunt
Nobody owns margin today. That's why it erodes. A system can't own a number. Assign a person, this quarter, before the ERP arrives.
AMG ERP Transformation | Confidential
6
Notes: If asked to rank them: data quality is the one that slips the date, SME capacity is the one that quietly decides whether the date was ever real, and cutover is the one that reaches the Board. Risk 6 is the one nobody wants to hear.

## Slide 7
6
Day 1 versus deliberately deferred
Deferral isn't a downgrade. It's how Day-1 scope stays small enough to land.
IN AT WAVE 1 · NON-NEGOTIABLE
GL, AP, AR, fixed assets, multi-entity, intercompany, consolidation, CAD/USD FX, US and Canadian tax
Item master, BOMs, routings, work centers, and a native ECN process. The engineering database retires here.
ETO order-to-cash end to end: quote, order, job, BOM, MRP, PO, production, ship, invoice
Procurement, receiving, inventory at cost
Shop floor time capture against job and operation. No labor on the job means no margin view, ever.
Job costing: estimate vs. actual, live
Aftermarket parts and service intake and billing. It's revenue. It doesn't get deferred.
Rev-rec exactly as we report it today, agreed with the auditors in M0-M2, not M11
DEFERRED BY DECISION, NOT BY DRIFT
CPQ and product configurator
Field service scheduling
Advanced planning and scheduling. Standard MRP first.
WMS, barcoding, portals, EDI expansion, advanced analytics, quality beyond basic NCR
CRM stays exactly where it is, untouched. A light account and order interface comes in the value phase.
HRIS and payroll stay siloed and post a summary journal
Customization discipline
Zero code at Day 1 is the target. An extension is approved only if it clears three questions: is the gap proven in the pilot on a real order, is it customer or regulator facing, and who owns it in five years? Where we'd otherwise customize, we change the process. That's the deal we sign when we go cloud.
AMG ERP Transformation | Confidential
7
Notes: The two bolded Day-1 items are the ones under pressure. Time capture will be attacked as 'we can add it later' and it is the exact reason the margin problem exists. Everything on the right gets a published Phase 2 backlog with a named owner, so it reads as sequenced rather than refused.

## Slide 8
7
Migration: what moves, and what doesn't
MOVES INTO THE NEW ERP
Active items; active BOMs and routings with activity in the last 36 months
Active customers and vendors
On-hand inventory at cost
Open POs, sales orders, jobs and WIP, AR, AP, ECNs
Opening trial balance, plus two prior fiscal years of GL at period-summary level for comparatives
STAYS OUT, BY DESIGN
Closed jobs
Historical GL detail and paid invoices
Superseded BOM revisions and historical ECN detail
Items dormant for three years or more
Anything whose only purpose is 'we might want to look at it'
The rule: history is a reporting problem, not a migration problem. We solve it with an archive, not with a load.
Legacy is extracted to a read-only cloud archive during design, kept live read-only for six months after the final wave as insurance, then decommissioned. Seven-year statutory retention is met by the archive. Nobody should be keeping a twenty-year-old ERP alive to satisfy an auditor.
AMG ERP Transformation | Confidential
8
Notes: The predictable challenge: 'we need ten years of history in the system.' Ask what decision they make with a closed job from 2011. The answer is always a report, never a transaction. Reports come from the archive.

## Slide 9
8
Reporting is built outside the ERP
That's what actually delivers uninterrupted access.
Legacy ERP
Sites not yet cut over
New cloud ERP
All entity finance + live waves
Read-only archive
20 years of legacy history
Warehouse
One conformed set of KPI definitions, mapped across both sources
Leadership KPIs
The 10 KPIs
Revenue
Gross margin
Contribution margin by job
Backlog
On-time delivery
Quote-to-order conversion
WIP aging
Inventory turns
Labor efficiency
Aftermarket attach
Defined and frozen in M0-M2, before anyone can argue the numbers changed.
Why outside, and not in the ERP:
Group reporting never comes from either ERP directly, so it survives every wave. The numbers don't quietly change on cutover weekend, which is the fastest way to lose executive trust in a new system. Reporting change requests freeze from mock cutover 2 through Wave 1 + 30 days. Expect a reporting dark period of about five business days at each cutover: we're saying so now rather than apologizing for it later.
AMG ERP Transformation | Confidential
9
Notes: This is the slide that answers the Board's 'uninterrupted access' mandate directly. The warehouse is cheap relative to the program and it is the only thing that gives a consistent number across a phased rollout. Building reports inside the ERP means rebuilding them at every wave.

## Slide 10
9
Month-end close continuity
We rehearse the close before we need it.
1
Time the cutover
Wave 1 lands at a fiscal quarter start. Not at year end. Not into an open close.
2
Rehearse it
Mock cutover 2 includes a full trial close in the new system on migrated data, signed off by the Controller.
3
Plan for slower
The first two live closes take longer. Book a three to five day extension, pre-book the auditors, run a close war room.
4
Keep a safety net
Legacy stays open for one close cycle after Wave 1 for restatement, then goes read-only.
5
Treat it as a control
Auditors engaged in M0-M2 on migration approach. The cutover is documented as a control event.
The close is the one thing the Board will notice if we get it wrong. So it's the one thing we practice twice.
AMG ERP Transformation | Confidential
10
Notes: If asked 'can you guarantee the close?' the honest answer is: we can guarantee we will have already done it once, on real migrated data, before the month that counts. That is as close to a guarantee as this work gets.

## Slide 11
What we need from you
Four decisions. None of them are technology decisions.
1
A sponsor who can say no
CFO or COO. Not IT. Someone with the standing to refuse a request from a peer.
2
Six SMEs, funded and ring-fenced
Named, backfilled, from month 0. This is the constraint that actually decides the date.
3
Date fixed, scope variable
If both are fixed, quality becomes the variable. Quality failures at cutover stop shipments.
4
An owner for margin
Not a system. A person. Named this quarter, before the ERP arrives.
Hold the date. Cut the scope. Own the margin.
Notes: Close on this. Every one of these is free, and every one of them is harder to get than the budget. If we leave the room with the sponsor and the SMEs named, the program is already in better shape than most.